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SO =  signing official certification, SKP = Senior Key Personnel, OP = Other Personnel, F-J = Material, direct, indirect, and fee costs, * to include appropriate % efforts,   †Subaward optional
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	Research Plan
	Letters of Support

	Introduction (resub)
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	Bkgrnd & Significance
	Prelim Studies
	Design & Methods
	Assurances
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-10 Days


Administrative deadline / prioritize letters


-3 Days


PIs (or all SKP + CSO) SIGN OFF &


SEND IN (5 grants takes about 10hrs on dDay)


-1Day


Correction of submission errors


+48hr


+4 Days


All PI/CSO Edits Due for final copy


Research Plan - 1st Drafts due to PI/CSO


PI's signoff on the download or withdraw it


Copy goes to Zak









